## Sheet1
PO ONLINE HOLDING BCC
PO ONLINE APROVEL / MARKET LIST / REQUEST NEW MENU
NO | DESCRIPTION | % | TANGGAL
|  |  | MARET | [9 empty] | APRIL | [29 empty] | MEI | [30 empty] | JUNI | [29 empty] | JULI
|  |  | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
PO ONLINE (WEB) | bar: MARET 22 to MARET 27; MARET 29 to APRIL 1; APRIL 3; APRIL 5 to APRIL 10; APRIL 12 to APRIL 17; APRIL 19 to APRIL 24; APRIL 26 to MEI 1; MEI 3 to MEI 8; MEI 10 to MEI 12; MEI 17 to MEI 22; MEI 24 to MEI 29; MEI 31 to JUNI 5; JUNI 7 to JUNI 12; JUNI 14 to JUNI 19; JUNI 21 to JUNI 26; JUNI 28 to JUNI 30
1 | - mengerjakan flow chart system , menu , SOP | 100 | bar: MARET 22 to MARET 23
2 | - login system . | 100 | bar: MARET 24
3 | - master user . | 100 | bar: MARET 25
4 | - master company . | 100 | bar: MARET 25
5 | - stock - view | 80 | bar: MARET 26
6 | - supplier - view | 100 | bar: MARET 26
7 | - level autorisasi | 100 | bar: MARET 27; MARET 29
8 | - Level ditambahkan level presdir | 100 | bar: MARET 30
9 | - Menu supplier di tambahkan NPWP | bar: APRIL 5
10 | - Menu level dimunculkan untuk semua user dan menampilkan nama2 user & nominal rilis nya | 100 | bar: MARET 31 to APRIL 1; APRIL 3
| FC = 0 - 2jt | 100 | bar: MARET 31 to APRIL 1; APRIL 3
| GM = 2jt - 25jt | 100 | bar: MARET 31 to APRIL 1; APRIL 3
| Presdir = >25jt | 100 | bar: MARET 31 to APRIL 1; APRIL 3
11 | - division view | 100 | bar: MARET 29
12 | - outlet view | 100 | bar: MARET 29
13 | - Pengerjaan Form Request PR Holding | 100
| - form request PR holding dan report | 100 | bar: APRIL 5 to APRIL 6
| - edit PR holding | 100 | bar: APRIL 8 to APRIL 9
| - list PR holding | 100 | bar: APRIL 10
| - approve PR Holding | 100 | bar: APRIL 10
- po dari approval PR Holding | bar: APRIL 12 to APRIL 17
14 | - Pengerjaan Form Market list | 100
| - form request Market list | 100 | bar: APRIL 6 to APRIL 7
| - edit Market list | 100 | bar: APRIL 8 to APRIL 9
| - listMarket list | 100 | bar: APRIL 10
| - approval Market list | 100 | bar: APRIL 12 to APRIL 15
15 | - Pengerjaan Form transaksi request new menu | bar: APRIL 19; MEI 10 to MEI 12
-form request new menu | bar: APRIL 20; MEI 10 to MEI 12
- edit request new menu | bar: MEI 17 to MEI 19
- list request new menu | bar: MEI 17 to MEI 19
- approve request new menu | bar: MEI 17 to MEI 19
16 | -master outlet | bar: MEI 20 to MEI 22
- create outlet (npwp, alamat, phone) | bar: MEI 20 to MEI 22
- edit outlet (alamat / phone) | bar: MEI 20 to MEI 22
17 | - master supplier | bar: APRIL 21
- tambah field supplier (npwp seperti contoh form dr pak agus) | bar: APRIL 22
- print form supplier | bar: APRIL 23
18 | Requestan / revisi 22 april 2021
- history pr di hal approval | bar: APRIL 24
- history log approve pr di list pr market/ holding | bar: MEI 4
- qty bisa d tambah, tdk bisa dikurangi utk approval pr holding (outlet manager) | bar: APRIL 26
- stock per departemen (pr holding) | bar: APRIL 26
- kode stock muncul di create pr, view, edit, approve | bar: APRIL 27 to APRIL 29
- dashboard per masing2 level user (request menu di hide utk user yg bukan product dev) | bar: APRIL 27 to APRIL 29
- hal approval dihilangkan kolom checklist approve | bar: APRIL 27 to APRIL 29
- approve button cancel item di ganti uncancel dan header diberi nama action | bar: APRIL 27 to APRIL 29
- total qty auto mengurangi jika item di cancel | bar: APRIL 27 to APRIL 29
- setting utk input backdate delivery order pr market list | bar: APRIL 27 to APRIL 29
- cost control sampai prsdir approval bisa mengurangi tp tdk bisa menambah qty (pr holding) | bar: APRIL 27 to APRIL 29
- harga pr holding muncul di cost control dan store keeper saat po | bar: APRIL 27 to APRIL 29
- pr marketlist harga muncul dan bisa di ubah | bar: APRIL 27 to APRIL 29
- pr-market list bisa upload nota | bar: APRIL 27 to APRIL 29
- request new menu level product dev, cc, fc, gm | bar: MEI 17 to MEI 19
- expired pr jika melebihi tgl do (pr holding) | bar: APRIL 30
- req menu pilih outlet / bisa multi outlet | bar: MEI 17 to MEI 19
- approval di pr market list hanya approve / cancel (tdk mengurangi qty / cancel per item) | bar: APRIL 30
- filteran by status PR | bar: APRIL 30 to MEI 1
'- report pdf PR | bar: MEI 3
- report pdf PO | bar: MEI 4
- PO filter by status | bar: MEI 4
19 | - trial and error | bar: MEI 24 to MEI 29; MEI 31
20 | - review | bar: MEI 4; MEI 24 to MEI 29; MEI 31
- term and condition di master company profile
PRESTO (DEKSTOP)
1 | - form budgeting | 100
| - input | 100
| - edit | 100
| - update | 100
| - report | 100
2 | - perhitungan stok akhir
- form kalkulasi stock
BACKEND QR RESTO APK
Promo (tb promo)
- create | bar: JUNI 1 to JUNI 2
- update | bar: JUNI 1 to JUNI 4
- read/ view data promo | bar: JUNI 4 to JUNI 5
- API GET data promo | bar: JUNI 4 to JUNI 5
* kolom image | bar: JUNI 4 to JUNI 5
* kolom ket (isi text promo berupa html) | bar: JUNI 4 to JUNI 5
* kolom aktif (0/1) | bar: JUNI 4 to JUNI 5
* kolom tgl_awal | bar: JUNI 4 to JUNI 5
* kolom tgl_akhir | bar: JUNI 4 to JUNI 5
* kolom dbinsert | bar: JUNI 4 to JUNI 5
* kolom id (berisi id promo bisa pakai UUID) | bar: JUNI 4 to JUNI 5
Membership (tb customer) | bar: JUNI 7 to JUNI 9
- API sign up member (POST) | bar: JUNI 7 to JUNI 9
- API update data member (PUT) | bar: JUNI 7 to JUNI 9
- API get data member (GET) | bar: JUNI 7 to JUNI 9
- view data member | bar: JUNI 9 to JUNI 10
- edit data member | bar: JUNI 10 to JUNI 12
Produk (tb produk) | bar: JUNI 11 to JUNI 12; JUNI 14 to JUNI 15
- sinkron image ke outlet | bar: JUNI 11 to JUNI 12; JUNI 14 to JUNI 15
- auto sync master product | bar: JUNI 11 to JUNI 12; JUNI 14 to JUNI 15
Guest comment (tb gcomment) | bar: JUNI 16 to JUNI 17
- view guest comment data | bar: JUNI 16 to JUNI 18
- API insert guest comment (POST) | bar: JUNI 18 to JUNI 19; JUNI 21 to JUNI 22
* kolom kd_cus | bar: JUNI 18 to JUNI 19; JUNI 21 to JUNI 22
* kolom ket | bar: JUNI 18 to JUNI 19; JUNI 21 to JUNI 22
* kolom nobill | bar: JUNI 18 to JUNI 19; JUNI 21 to JUNI 22
* kolom dbinsert (datetime) | bar: JUNI 18 to JUNI 19; JUNI 21 to JUNI 22
* kolom nilai (berisi 1-5) | bar: JUNI 18 to JUNI 19; JUNI 21 to JUNI 22
* kolom kd_kantor | bar: JUNI 18 to JUNI 19; JUNI 21 to JUNI 22
Term Condition (masuk k tb setting) | bar: JUNI 23 to JUNI 25
- master data (CRUD) | bar: JUNI 23 to JUNI 25
- API get term condition (GET) ( html ) | bar: JUNI 23 to JUNI 25
Outlet (tb acc_dept) | bar: JUNI 25 to JUNI 26; JUNI 28 to JUNI 30
-API get data outlet (GET) | bar: JUNI 25 to JUNI 26; JUNI 28 to JUNI 30
- edit data outlet (status outlet dan logo outlet) | bar: JUNI 28 to JUNI 30
* tambah kolom logo
* tambah kolom aktif = 0 atau 1
Company Profile (tb public_parameter)
- API get data company (GET)
History Transaksi (tb listbill)
- API get data transaksi (GET)
APK QR AND MEMBER
splash
spash screen | bar: MEI 10
auth
signup | bar: MEI 11 to MEI 12; MEI 17 to MEI 18
login | bar: MEI 19 to MEI 21
main
main page | bar: MEI 22; MEI 24 to MEI 29; MEI 31 to JUNI 2
guest comment popup | bar: JUNI 3
menu section | bar: JUNI 4 to JUNI 5; JUNI 7
outlet section | bar: JUNI 8 to JUNI 10
promo | bar: JUNI 11 to JUNI 12; JUNI 14
qr scaner | bar: JUNI 15
order
order page | bar: JUNI 16 to JUNI 19; JUNI 21 to JUNI 26
profile | bar: JUNI 28 to JUNI 30
main profile | bar: JULI 1 to JULI 3
history | bar: JULI 5 to JULI 6
term & service | bar: JULI 7
about | bar: JULI 8
edit profile | bar: JULI 9 to JULI 10; JULI 12 to JULI 14

## Sheet2
NO | DESCRIPTION | Progress (%)
PO ONLINE (WEB)
1 | - mengerjakan flow chart system , menu , SOP | 100
2 | - login system . | 100
3 | - master user . | 100
4 | - master company . | 100
5 | - stock - view | 80
6 | - supplier - view | 100
7 | - level autorisasi | 100
8 | - Level ditambahkan level presdir | 100
9 | - Menu supplier di tambahkan NPWP
10 | - Menu level dimunculkan untuk semua user dan menampilkan nama2 user & nominal rilis nya | 100
| FC = 0 - 2jt | 100
| GM = 2jt - 25jt | 100
| Presdir = >25jt | 100
11 | - division view | 100
12 | - outlet view | 100
13 | - Pengerjaan Form Request PR Holding | 100
| - form request PR holding dan report | 100
| - edit PR holding | 100
| - list PR holding | 100
| - approve PR Holding | 100
- po dari approval PR Holding
14 | - Pengerjaan Form Market list | 100
| - form request Market list | 100
| - edit Market list | 100
| - listMarket list | 100
| - approval Market list | 100
15 | - Pengerjaan Form transaksi request new menu
-form request new menu
- edit request new menu
- list request new menu
- approve request new menu
16 | - trial and error
17 | -master outlet
- create outlet (npwp, alamat, phone)
- edit outlet (alamat / phone)
18 | - master supplier
- tambah field supplier (npwp seperti contoh form dr pak agus)
- print form supplier
PRESTO (DEKSTOP)
1 | - form budgeting | 100
| - input | 100
| - edit | 100
| - update | 100
| - report | 100
2 | - perhitungan stok akhir
- form kalkulasi stock